## Ark1
|  |  | WEEK 1: 02.-06.03.2020 |  |  |  |  | WEEK 2: 09.-13.03.2020 |  |  |  |  | WEEK 3: 16.-20.03.2020
Tasks | Resources | Status | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
Managing project | PM |  | Planing, organizing project team, monitoring progress, keeping contact with the customer
Customer meeting | PM, Designer, FED, Customer |  | * |  |  |  |  | * |  |  |  |  | *
Kick-off meeting | Whole team |  | *
Status meeting | Whole team | [6 empty] | * |  |  |  |  | *
Presentation and lounch | PM, Designer, FED, Customer
Design/Layout/Text
The Promise headline | Designer
Online order form and prices | Designer
Contact form and information | Designer
About us page:
Company identity | Designer,Copywriter
Production chain | Designer,Copywriter
Call to action buttons | Designer, FED
Social media links | Designer
Reviews | Designer,Copywriter
Newsletter | Designer,Copywriter
Photography
Photos of the products | Photographer
Photos of personal/Company | Photographer
Edit Photos
Coding
The Promise headline | FED
Online order form and prices | FED
Contact form and information | FED
About us page:
Company identity | FED
Production chain | FED
Call to action buttons | FED
Social media links | FED
Reviews | FED
Newsletter | FED
UX/UI tests | FED
Tests:Plattform and Browser | FED
Adjustments | Whole team
Safety margin
Team members:
PM = Project Manager
Designer
FED = Frontend Developer
Photographer
Copywriter
* = 1-2 hours